## Sheet1
Institute for Global Health
Proposal Submission Timeline
Sterling: PAR-16-254 Mechanisms of Mycobacterial-Induced Immunity in HIV-Infected .. TB … (R01) due 1-11-2018 (OSP submit)
Days in Advance of Submission Deadline
|  | Responsible Party | Task At Hand
| 2 months | Principal Investigator | Notify Grants Manager (GM) and/or Grants Team member via email of your intent to submit application on specific date.
Business Days
| 60 | Principal Investigator | 1) Submit REDCap Intent to Submit (link provided). 2) Complete REDCap Survey 2 that lists all personnel with proposed effort, consultants, and equipment as well as subcontract(s) associated with the proposal.
2017-10-11
| 45 | Principal Investigator | Complete REDCap Survey 2 that lists all personnel with proposed effort, and consultants associated with the proposal.
2017-11-01
| 30 | Principal Investigator | PI informs GM of any changes from REDCap Survey 2 associated with the proposal.
2017-11-20
| 24 | Grants Manager | Using the information from REDCap Survey 2, GM will submit a draft budget to PI
2017-12-01
| 18 | Administrative Assistant | GM will work with AA to have draft Biosketches prepared for PI to review and edit.
2017-12-11
| 18 | Principal Investigator | 1) PI to return draft budget with changes to GM. 2) PI to provide draft of Budget Justification and Facilities/Equipment section of proposal.
2017-12-11
| 10 | Grants Manager | FINAL COMPONENTS for Coeus Approvals: (Budget, Budget Justification, signed LOIs, Project Narrative, Project Summary/abstract, Targeted Planned Enrollment Table, and PHS Assignment Information). DRAFT bios and Facillites are also needed. Proposal will be uploaded and validated by GM for internal reviews/approvals.
2017-12-20
| 6 | Principal Investigator | FINAL REMAINING COMPONENTS: Research Plan (Research Strategy, Aims, etc.) to GM to upload in Coeus.
| 2017-12-27 | Dr. Sterling aims to complete everything by COB on 12/22, but 12/27 will be the drop date
| 3 | Principal Investigator | When proposal is approved by the Office of Sponsored Programs (OSP) office, 1) PI will meet with GM to review all final documents together in Coeus. 2) PI will electronically submit grant to NIH 3 business days PRIOR to ACTUAL submission deadline date.
2018-01-08
3 days PRIOR TO ACTUAL SUBMISSION DEADLINE PROPOSAL MUST BE SUBMITTED